## Slide 1: Update on reemployment services
Employment Security Advisory Committee
October 26, 2020

## Slide 2: Equitable Access for Customers
Approach
  Build out virtual services to serve as many people virtually as possible
    Phones
    Live chat
    Online scheduler
    E-services training
  Prepare WS offices for safe in-person service delivery
    Drive those with virtual capability to virtual services
    Focus limited in-person space for those with digital access barriers
    Implement all required safety protocols
    Train staff
  Use safe outreach
    Completed an Outreach Safety Plan
    Go to those who can’t come to us
    Supplement limited capacity in WS offices

## Slide 3: Building Virtual Services
Technology
  Phones
    Implemented adjustments to all local WS numbers to be answered by live agents (on site or teleworking) in all areas. (Transitioned off State-wide UI-linked number).
    Expanding to more live agents.
    Exploring data reporting options.
  E-services/chat
    Open recruitment to hire multiple live-chat agents.
    Trainings on MS Online tools.
    Trainings on virtual collaboration tools (Webex, Zoom, Skype, etc.).
  Scheduling tools
    Existing scheduling tools not scalable.
    Gathering requirements now for state-wide scheduling tool.
    Local areas working on temporary scheduling options.
  Virtual Job Fairs
    Have been completing Job Fairs through the Brazen platform.
    Researching other more cost-effective long-term options to keep them going.
    Maintaining the structure flexibility to prove by area, by industry, by job seeker, and state-wide experiences.

## Slide 4: Preparing WorkSource Offices
Progress on safety and planning checklists
  Physical alterations mostly complete
    Two state-wide preparation trips completed by ESD Distribution Center Staff
    PPE stocking complete
  Operational planning ongoing
    Partnering with Workforce Development Councils
    Modify customer service processes
    Customer Flow / Occupancy Monitoring / Contact Tracing
  Reviewing contractual needs
    Modified janitorial support
    Potential Security needs
  IT Hardware update nearly complete
    New public copies, scanners and faxing machines installed
    New public computers completed on eastside, westside completes next week

## Slide 5: Preparing Staff
  Completed staff return from UICS support
    Refresher program and services trainings.
    Trainings on new virtual services.
  Identifying UI ambassadors
    Leverage all the time and effort to train EC staff on UI.
    Staff who can provide additional UI services for customers with both UI and Reemployment Needs.
  Increasing staff support
    Wellness and Vicarious Trauma trainings and resources.
  Increasing staff to meet demand
    Have developed initial staffing increase numbers.
    Aligning hiring/onboarding with demand.
    Training staff to areas of higher demand.

## Slide 6: Partnership and Alignment
At the State-level
  Program services
    Aligning the restart of RESEA with emergency rule considerations
    More outreach in rural communities and MSFW
  Results Washington
    Partnering to align with new goals and initiatives
  Washington Recovery Group
    Alignment between agencies, organizations
    Alignment between initiatives and outcomes

## Slide 7: Questions?